## Slide 1
PROMOTING
YOUTH EMPLOYMENT IN REMOTE AREAS IN JORDAN / JOB-JO
Action Plan
Dr. Mohammad Almajali
20-21.02.2022

## Slide 2: Overview
The project is extended until mid of August
The extension was based on activities
Training of Students
Training of staff
Visit to BSNBs by EU partners
Conduct physical meeting
Online training UCY
Final conference

## Slide 3: Objectives
1. Establishment regional Business Service Network Bureau (BSNB) to promote employment in the provinces of Karak, Tafila, Maan, Aqaba and Irbid.
2. Development of training courses in the BSNB based on the experience exchange with the EU.
3-Producing training material
4- Students and staff from JO partners will receive training in EU

## Slide 4: How the project objectives will be achieved?
Establish Business Service Network Bureau inside academic institutions and prepare it to receive the necessary equipment provided within the framework of this project.
All JO partners provided the required official letter stating that the place is allocated
Equipment were distributed and BSNBs were inaugurated

## Slide 5: Staff Training
Conduct training that focuses on methods of teaching and development of the methodological foundation for the trainers assigned in these Bureaus.
UCY presented the whole training session
Need to specify other training during this meeting
Training at ISLA (end of March)
Number and quality of trainees

## Slide 6: Training at ISLA
Message from ISLA
Trainees are people linked to the direct work of BSNB, so that there is an exchange of experiences on the difficulties and for the joint definition of improvement strategies.
Required: list of trainees, including their academic qualifications and their role at BSNB. List the problems they feel in the work of the BSNB and that they bring this document with them, or, preferably, that these summaries are sent to us before the training.
Female and different people

## Slide 7: Students Training
In UCY and Germany
4 from each University
Male and female
Dates after end of this semester (14 days)
Topics to be offered by UCY and INT@E and HTWAK

## Slide 8: Visits to BSNBs
Conducted by ISLA
Need another visit by Germany
One from INT@E and one HTWK
Dates should be specified by the end of this month

## Slide 9: Online training
Need to continue on online training
UCY has to arrange such training by EU partners
Three per month

## Slide 10: Final conference
Location in Jordan (MU or TTU)
Date (early July)
Need progress report from each partner including financial
Each partner presents activities
WP leader should present the WP
Invitation will be sent end of May

## Slide 11
THANK
YOU